Corporate Plan Objectives for 2014-2017

I.	TO PUT RESIDENTS AND SERVICE-USERS AT THE HEART OF WHAT WE DO

|  | Objective | Targets and Initiatives | Target achieved? (Y for Yes, N for No, or P for partially achieved | Comments |
| --- | --- | --- | --- | --- |
| a. | To show continuous improvement on residents’ satisfaction with the Repairs & Maintenance service. | Our target is to be in the top quartile on “satisfaction with the way the landlord deals with repairs and maintenance” for our London peer group. | N/A | Although Richardson were contracted to provide this information, they failed to do so in the first 8 months of the year. Our interim contractors are not linked electronically so are unable to do so for the remaining four months. We therefore have no statistically reliable data to report. We are now reverting to our own in house phone surveys to remedy. The new OJEU tender will make this a contractor requirement going forward. |
|  |  | Our target is to ensure we continually improve our overall satisfaction target year on year, and incorporate best practice in the way we deliver our repairs. | N/A | See above. |
| b. | To increase and improve the ways that residents can work with Hexagon to help us improve services. | Support residents on the Performance Review Group (PRG) to monitor performance and targets to improve service delivery, accountability and value for money. | P | Scrutiny training being arranged for late May |
|  |  | Roll out a programme of at least two residents’ inspections a year which will assess the process of service delivery from a residents’ perspective. | P | One inspection reported during the year, namely cyclical decorations, with Community Investment currently underway. |
|  |  | Develop the Residents’ Repairs Group so that residents scrutinise the delivery of the repairs service with the aim of driving improvements to the service | P | Scrutiny training being arranged for late May. In addition, training on procurement is also being planned |
|  |  | Provide and publicise new involvement activities which are geared towards scrutinising performance delivery. | P | Involvement Matters info flyer to go out with TBM ballot forms in July |
| c. | To get things right the first time, or if we don’t, to deal better and more efficiently with complaints. | In 2014/15 at least 90% of complaints are responded to on time and do not escalate (rising to 92% in 15/16 and 95% in 16/17). | N Y | 65% performance in responding on time achieved 92% did not escalate |
|  |  | To log all complaints within 24 hours of receipt. | Y? | No performance measure on this but Complaints inbox is dealt with daily and gets priority over other inboxes. . |
| d. | To ensure all our homes are subject to an ongoing home improvement programme. | We will ensure that 100% of our stock is fully embedded into our Lifespan Data tool. | P (ongoing) | Approximately 300 units remain to be accessed On data transfer, synchronising between Genero/Lifespan to bring NB units is outstanding. |
|  |  | A rolling 5 year programme of activity is refreshed annually making adjustments for Stock Condition Survey results. | Y | The annual Stock Improvement programme is primarily derived from the results of the stock condition surveys. |
|  |  | 20% of our stock will be inspected / reviewed every year to ensure all properties are benefitting from improvements. | P | The 2007 surveyed stock were refreshed in 14/15. In 15/16 we will refresh the data for 2008 before commencing the 20% from 16/17 |
| e. | To ensure all our homes meet statutory health and safety regulations. | We will ensure all of our contractors meets all relevant H&S requirements (including Gas Safety) and be able to advise us of any H&S issues identified during the course of their activities. | Y | Gas Safety was 100% at year end. All contractors are aware of our requirements and we are in receipt of their own H&S policies and procedures. |
|  |  | We will ensure that all relevant Fire Risk Assessments are up to date with actions identified completed within acceptable timescales. | Y | A new PI is now in place to track FRA reviews and the action points arising out of them. We are now using Lifespan to report on the completion and actions. |
|  |  | That all properties are surveyed and clearly identified for potential asbestos where relevant undertaking removal if required. | P | Programme on site to survey all communal areas pre 2001 to complete information held to meet compliance. |
|  |  | We will have less than 2 statutory notices per year maximum. | Y | We are aware of only one notice received during year. |
| f. | To improve residents’ satisfaction with Estate Services. | Our target is to carry out annual satisfaction surveys of our cleaning and gardening services and aiming for a minimum of 75% satisfaction by 2017, increasing throughout the life of this plan to 65% in 2014, 70% in 2015 and 75% by the end of 2016. | N/A | The previous survey (2014) gave a satisfaction level of 61%. The next survey has not yet taken placed but is now due Sept/Oct 2015. We hope that the work of the new post of Estates Contracts Monitor will show in the results. |
|  |  | We will implement the recommendations of the Estate Services Review by the end of 2014/15. | P | Work on the recommendations of the review is well underway and much of it is done. A big item is the review and re-tender of the cleaning and grounds maintenance contracts. This is a major project involving EU Procurement rules and has been delayed due to the technical and staffing resources needed but work is now well underway and the procurement process will be underway by the end of June. |
| g. | To ensure all Co-ops meet Hexagon’s standards. | Maintain the risk-based monitoring of managing agents’ performance to ensure that it does not fall below the levels for Hexagon managed homes. | Y | Quarterly monitoring in place. Schedule of annual monitoring visits for 2015 in place and due to be completed by Nov |
|  |  | Ensure that all managing agents provide up to date gas safety certificates and carry out Fire Risk Assessment (FRA) reviews. | Y | At year end all co-op gas safety certificates were in place. All co-op FRA Reviews up to date |
|  |  | Carry out a residents’ satisfaction survey of all agency managed residents. | P | Survey about to get underway. |
| h. | To provide excellent care services which are highly rated by service users and regulators. | When inspected, CQC registered services will meet all assessed standards, and our Supporting People regulated service will achieve Level A. | Y for both Nursing Homes N for one SH scheme | In April 2014 Woodcote Road had an unannounced inspection and fully met the assessed standards. Townley Road was last inspected in December 2013 when it also met all assessed standards. Newstead Road was last inspected by the local authority under the Quality Assessment Framework in March 2013 when it was assessed as overall B where the report said ‘Newstead Rd is an excellent service that is moving towards an overall A rating’. |
|  |  | To achieve a service user satisfaction rating of 80%. | Y | In our high support services in 2014-15 overall Satisfaction was 82%, an increase of 12% compared with 2013-14. |
| i. | To innovate and invest in Community Investment initiatives. | We continue to invest in the Hexagon Academy, supporting residents back into employment. | Y | See detail below |
|  |  | 65% of residents registered with the Academy to report a positive outcome (further learning, employment, volunteering, new business start up). | Y | Average 60 to 65% of residents report positive outcome |
|  |  | At least 20 residents into employment each year. | Y | 23 residents into employment for 14/15 |
|  |  | To achieve Fair Train Work Experience Quality Standard Gold level by 2015/16. | P | Fair Train Work Experience Quality Standard Silver level awarded in January 2015. On track for submission for Gold level September 2015 |
|  |  | To launch a new Youth Employment programme in 2014/15 providing employability support and training for young residents aged 15 to 24. | Y | Programme launched. 9 young people completed boot camp, 5 completers have since secured employment. 15 young people registered on programme, 8 of 15 remained on programme, 3 of which are on multi trade apprenticeship schemes |
|  | To support our low-income residents to ensure they are maximising their income and help reduce their spending | We will continue to provide general and 121 money advice to help residents receive income they are entitled to. | Y | Provided 1-2-1 support for 90 residents (17 of which affected by bedroom tax or benefit cap. £112405 of income generated for residents in 14/15, of which £97146 came directly back to Hexagon as DHP / HB |
|  |  | To work closely with residents to enable households to make changes to reduce household expenditure e.g. by learning new DIY skills. | Y | Circa 50 residents attended Moneyopoly – money advice at Residents Day designed to offer practical ways to reduce household expenditure. 18 residents attended sewing courses in partnership with WEA held. Courses have an element on learning new skills to help save money i.e. take up curtains, repair clothes. Furniture upcycling and DIY painting courses arranged in partnership with Bell Group. But demand was very low and courses not held. |
|  |  | To support residents to get online in order to benefit from on-line purchasing with a target of 40 in 2014/15 | P | 26 residents completed training and now online Digital Communications survey identified 50 residents and Winter Warmth packs identified 34 residents interested in computer training and work now underway to arrange training for these residents. |
|  |  | To develop in 2014/15 a ‘Pennywise Power’ programme to help residents reduce their spending on fuel. | Y | Worked in partnership with Stock Improvement to deliver Winter Warmth and Green doctors schemes. 200 residents benefitted from energy advice and measures |
| j. | To work closely with our residents to ensure a smooth transition for Welfare Reforms, especially Universal Credit. | To implement the welfare reform response plan with a focus on improving digital inclusion in 2014/15. | Y | This plan is updated several times a year. The specific digital inclusion elements are being implemented. |
|  |  | To develop in 2014/15 more pro-active, partially automated arrears management tools. | N | A decision was taken to postpone this work item due to the slippage of the timetable for the introduction of UC. Work is now underway with initial meetings with suppliers of potential services being arranged. |
|  |  | To promote our partnership with the London Plus credit union. | Y | Partnership with London Plus Credit Union promoted Credit Union launched at Residents Day, promoted at Residents Day and through Home News. Briefing sessions held for different staff teams on credit union and how it can benefit different client groups. Small numbers of residents have signed up to the Credit Union. Promotions campaign to commence shortly |
|  |  | To investigate in 2014/15 the cost-effectiveness of new rent payment methods for residents moving onto UC. | N | This was given a lower priority during 14/15 because of the slow implementation timetable for UC and the slow pace of developments in the market. We will keep a watching brief on the market which there are now signs that it may be developing. |
| k. | To develop our Customer Contact Strategy to drive improvements in the way we engage with residents, including increased use of digital communications. | Strategy agreed by the Board in summer 2014. | N | Strategy to be presented to the Board in May 15. |
|  |  | Engagement with residents to agree new service standards for digital communications during 2014. | P | 1st Focus group held in April 15 More to follow in next few weeks |
|  |  | Develop internal systems and staff capabilities to allow greater use and recording of emails, texts and social media communications over life of the plan. | P | This is in action plan of the strategy for implementation in 15/16 |
|  |  | Increase residents’ use of digital communications, with targets outlined in the Board approved strategy. | N | As above |
| l. | To respond innovatively to the needs of Hexagon’s tenants who are overcrowded. | Our target is to increase the numbers of overcrowded tenants we re house by pursuing under occupation initiatives that release larger homes that are subsequently available to Hexagon transfer applicants. This will include tenants affected by bedroom tax. | P | Bedroom tax affected tenants continue to receive special priority but as a cohort are generally not interested in down-sizing. The decision by SELHP to end the sub-regional down-sizing project in July 2014, removed the only resource dedicated to this work. |
|  |  | Should there be any opportunities for loft conversion, these will be targeted at overcrowded households. | N | Unsuccessful bid for GLA funding. |
|  |  | We will strive to maintain our 25% share of new lettings and re-lets and target these at overcrowded households. | P | We have maintained this where we can. Recent new developments have been in Croydon however, where the 25% agreement is not in place as this brought is the only borough not part of the SELHP lettings agreement. |
| m. | To determine and implement the approach to the Government’s ‘Staying Put’ proposals. | Proposals to be put to Hexagon’s Board once details of Government’s approach are available. | Y | The Board decided not to implement Pay to Stay in January 15. |
| n. | To utilise our Stock Improvement funding to leverage additional funding that will help residents fight fuel poverty. | To ensure that a minimum of 45% of the budget is spent on energy efficiency improvements across the programmes. | Y | We believe we are easily achieving this target and a review is currently underway with Parity Projects to re-confirm spend on current and projected programmes in line with our Greening the Stock action plan. |
|  |  | To meet the objectives set out in the sustainability action plan. | P | All objectives are being actively progressed with targets monitored and reported to the Board on an annual basis. Objectives are timed and monitored until completion with time revisions if required. |
|  |  | To meet the objectives set out in the Greening of the stock action plan. | Y | Progress with the plan is on track; objectives are being tracked and discussed at our Sustainability Group meetings. |
|  |  | To work closely with Resident Involvement in developing Green Champions and beacon homes. | Y | Meetings have taken place, training plans have been drawn up, and recruitment is nearing completion, ready for launching later in the next quarter. |
| o. | To further roll out and embed our ‘Customers At The Heart’ programme. | We will consistently promote Customers at the Heart throughout the Organisation, via the Customers at the Heart (CATH) Working Group Action Plan. | Y | The CATH Group working has met regularly and implemented all of the actions as planned |
|  |  | We will develop a ‘Customers at the Heart’ Induction Session for all new employees by July 2014. | Y | CATH Induction Session added to Core Courses and all new employees attend. |
|  |  | We will provide Customers at the Heart training for all Care Homes staff by June 2014. | Y | One day session delivered by MGI to all Care Homes staff. |
|  |  | To consistently maintain a service level of 80% for telephone responses in Customer Services. | P | Target was met for 2 of the 4 quarters (including Q4) but poor performance from repair contractor resulted in increased call volumes and a missed target for 2 quarters and the full year therefore ended at 77.3% |
|  |  | To implement by the summer of 2014 a call recording system in Customer Services and Housing Services to monitor the quality of service delivery on the telephone. | Y | Call recording has been implemented and is in use for monitoring that informs training and coaching as well as complaint resolution. |

II.	TO CHANGE OUR WAYS OF WORKING TO ACHIEVE MAXIMUM EFFICIENCY

|  | Objectives | Targets and Initiatives | Target achieved? (Y for Yes, N for No, or P for partially achieved | Comments |
| --- | --- | --- | --- | --- |
| a. | To minimise our rent arrears and maximise our rent collection. | Our target is to ensure that Hexagon’s performance for rent arrears is in the top quartile for the London peer group. | N | 4.7% for Y/E 2015 vs. top quartile of 3.8% (for 13/14) |
|  |  | We will develop the use of partially automated rent arrears management tools to streamline rent collection and arrears actions, so releasing resources for more individual casework as preparation for the introduction of UC. | P | A decision was taken to postpone this work item from 14/15 due to the slippage of the timetable for the introduction of UC. Work is now underway with initial meetings with suppliers of potential services being arranged. |
|  |  | We will review staffing structures to ensure we are working as efficiently as possible in readiness for the introduction of UC. | N/A | This work is not scheduled to take place until 2015/16. |
| b. | To minimise the number of days it takes to re let our general needs homes. | To keep void losses below 0.8% of the rent roll, with the aim of continuously improving each year during the life of the plan. | Y | Void loss for 14/15 was 0.76% |
|  |  | To ensure our general needs void turnaround target of 33 days is achieved (i.e. within the top quartile). | N | Void turnaround at the end of 14/15 was 40 days. Top quartile data is not yet available but this is very unlikely to be top quartile performance. Work is ongoing to improve turnaround times. |
|  |  | We will work with LAs to obtain multiple nominations to void units as much as possible. | Y | This is now happening for most voids. |
|  |  | We will develop improved systems for monitoring and managing performance at key stages within the allocations process. | Y | Work has been done which makes it much easier to identify performance at key stages and this info is being used to manage performance. |
| c. | To minimise the number of days it takes to re let our supported housing homes | We will minimise rent loss from voids (which are not funded by commissioners) and achieve our voids target of 4.3% in 2014/15 and continuously improve over the life of this plan. | N | In 14/15 the void loss not funded was 7.5%. However the majority of this was at Wolsley [now sold] and Queens Road [where we have a funded agreement for 15/16] and the void loss without these schemes is 1.4%. Given this we hope to achieve the target in 15/16. |
| d. | To maximise the recovery of service charges | Our target is to recover 100% of service costs, including staff costs. | N | There was a substantial overspend on service costs in 2014/15 which is reported in further detail in the Q4 Mgt accounts |
| e. | To develop alternative plans for low demand supported housing where this becomes an issue or where accommodation is no longer strategically relevant. | We will explore options and remodel schemes where it is financially feasible to do so. We will dispose of schemes assessed as not viable. | Y | During 14/15 we disposed of Wolsley and remodelled Queens Rd [see c. above] |
| f. | To exercise strong control over day to day repair costs. | Our target is to deliver the responsive repairs spend within budget each year. | P | Responsive repairs was overspent by £385k following Richardson termination, interim contractor appointments, and variation order control challenges. |
| g. | To implement the 3-year ICT strategy, including the Information Flow (IF) Project. | Deliver the benefits of the IF Project in line with the programme timetable. Deliver key infrastructure improvements by the end of March 2015: implement a new phone system implement a virtual PC environment and upgrade our Office software Deliver the IT aspects of the Customer Contact Strategy in line with the timetable outlined in that strategy. Deliver business efficiencies by providing: an integrated arrears management system (by March 2015) electronic document management for new tenancy records (by March 2015) tablets for Housing Officers and the Responsive Repairs team (by September 2014) other business software as required by the ICT Strategy | P P P Y N N P Y | The complaints system has been enhanced; defects redesigned and repairs improvements introduced; the project has been closed and the undelivered phases will be considered by the BIT New phone system has been procured; due to go live June 2015 Network and core infrastructure has been replaced to underpin this project. Virtual PCs have been successfully piloted; rollout to complete by June 2015 Email and texting from Genero is a key project on the 2015/16 workplan. Arrears tool due to be implemented by Feb 2016 EDM evaluation has been transferred to the new Business Improvement team Laptops have been successfully piloted and will be delivered to surveyors by May 2015 and Housing Officers by June 2015 Call recording in place for CSC and Housing Services; Sun finance system upgraded; BACS in place saving money on creditor payments |
| h. | To implement the Asset Management strategy. | We will review the strategy’s performance annually with the board, refreshing it every three years in line with the corporate objectives and ensuring it is a live document and supports all cross cutting activities such as the sustainability strategy, greening the stock and our disposal requirements. | Y | The strategy updates have been reported to the Board with good progress over the past year. We have identified new elements to be added when the next 3 year plan is drawn up later this year. |
| i. | To support our staff with first class training to deliver our objectives. | During each year of this plan we will develop a detailed training plan for the Organisation, which includes training objectives and costings. | Y | Training Plan developed and 6 monthly progress report considered by DG. |
|  |  | Our target is to provide funding for all training that is identified as necessary to achieve our corporate objectives outlined in the plan. | Y | Training identified has been delivered. |
|  |  | During each year of this plan, we will develop a formal annual review of the training plan, including outcomes, to ensure that our training is effective and provides value for money. | P | Formal annual review due in June 2015. |
| j. | To renew and refresh our Investor in People status. | Our objective is to achieve Investor in People Gold Status at our next Review in 2015. | N/A | Review not yet undertaken but will commence May 20th. |
|  |  | We will implement the SMART targets arising from the previous IIP Review in 2012, and continuously communicate progress with staff members. | Y | IIP Actions implemented. |
| k. | To carry out an annual programme of service quality improvements which focus on trouble-shooting service areas that require innovation and improvement. | Review three areas a year, which require improvements, throughout the life of the Corporate Plan and implement the Action Plan arising from the findings. | P | During 2014/15 this included work on sickness absence management and empty homes. This are of work will now be significantly increased with the creation of the new Business Improvement team, with two new staff members |
| l. | To be open-minded about new ways of working and organisational structures if this will assist in improving service delivery to residents. | We will assess any possible merger opportunities that arise during the life of this Plan against what such a merger would do to benefit existing and future tenants. | Y | Following the Board’s decision in March 14 to not seek a merger partner, we have received no further approaches. |

- TO ENSURE THAT HEXAGON CONTINUES TO GROW IN A FINANCIALLY, SOCIALLY, AND ENVIRONMENTALLY

SUSTAINABLE MANNER

|  | Objectives | Targets and Initiatives | Target achieved? (Y for Yes, N for No, or P for partially achieved | Comments |
| --- | --- | --- | --- | --- |
| a. | To use our existing assets to continue to grow and provide new homes for those in housing need. | Secure grant funding from the GLA for the 2015/18 development programme to deliver 200 new homes. 120 of which are for rent (60 at discounted rents and 60 at capped rents) and 80 of which are for shared-ownership sale. | Y | Grant secured from GLA to fund 2015/18 development programme |
|  |  | Deliver the remaining 253 new homes in the existing programme (11/15 & the Mayor’s Covenant, Building the Pipeline). | P | 100% of the reduced 213 unit 11/15 programme is completed. Those schemes that could not meet their 11/15 target have been moved to the MHC BTP. We anticipate that all BTP schemes on site will be delivered by Mar 16’, ahead of the contractual march 18’ deadline |
| b. | To provide a range of subsidised rented housing to those for whom home ownership or market renting is not financially possible. | Develop 120 rented homes over the 2015/18 GLA funded development programme period: 60 at discounted rents and 60 at capped rents. | P | Of the 2015/18 programme, 6 discounted rented homes are currently on-site. The remainder of the programme is still to be secured. |
|  |  | Deliver the remaining 194 rented homes from GLA funded programmes. | P | Largely dependent on start on site dates. Its understood that the strategy to secure sites will focus on those with planning from Sept 15’ in order to achieve targets |
| c. | To meet the housing needs of those who wish to become home owners, but who cannot afford to purchase outright in the open market. | Secure grant funding from the GLA for the 2015/18 development programme and deliver at least 40% / 80no. shared-ownership homes, subject to market conditions. | P | Grant funding for 80 shared-ownership homes has been secured – 80 plots need to be identified and secured to deliver these homes |
|  |  | Deliver the remaining 49 shared ownership homes from existing GLA funded programmes. | P | Largely dependent on start on site dates. It’s understood that the strategy to secure sites will focus on those with planning from Sept 15’ in order to achieve targets |
| d. | To meet the housing needs of those with larger families. | Secure grant funding from the GLA for the 2015/18 development programme to deliver 36% of rented units as 3 bed (or more) sized homes. | Y | Grant funding has been secured from the GLA to develop these homes under the 2015/18 programme |
|  |  | Deliver the remaining 72 three bed homes from existing GLA funded programmes. | P | Largely dependent on start on site dates. It’s understood that the strategy to secure sites will focus on those with planning from Sept 15’ in order to achieve targets |
| e. | To produce additional cross subsidy for our new build social housing programme by developing housing for outright sale. | Identify and secure land to develop circa 30 homes for outright sale during the 2015/18 development programme period, in line with our investment policy. In recognition of the risks to Horniman HA, our non-charitable subsidiary this activity will be subject to rigorous market assessment. | P | Five plots have been identified for homes for outright sale. |
| f. | To build mixed, sustainable communities. | Seek to deliver mixed-tenure developments where more than 25 units are constructed on one site: Provided the market conditions for home ownership development are right and in accordance with Local Authority priorities and requirements | Y | Where financially viable, we are developing mixed-tenure schemes on sites where there are in excess of 25 homes. |
| g. | To be an efficient and effective house builder. | Our target is to deliver all our new schemes on time, on budget & in accordance with internal approvals. | Y | 14/15 schemes- Total scheme costs as % of that approved by Risk Appraisal Panel at start on site equates to 99.48%. This is within our target of 100% or less. We have successfully delivered the reduced 11/15 AHP and are on target to complete the MHC BTP in March 16’ |
|  |  | We will use annual assessments of contractors & consultants to achieve high quality service & deliver continuous improvement. | Y | We continue to use a suite of KPI that inputs into the annual review. The latest review identified a contractor & consultant that we chose no longer to work with due to underperformance. |
| h. | To maintain our position as a GLA Investment Partner that delivers. | Our target is to achieve all our annual GLA targets, including expenditure, starts on site & completions and achieve delivery forecast dates and to specifically deliver 11/15 funded schemes by 31st March 2015, Mayor’s Covenant schemes and MHC 15/18 funded schemes by March 2018 Our target is to achieve the conversion income required to fund our MHC 15/18 funded programme & existing programmes by: Reletting a proportion of our existing properties at ‘market related’ rents and Disposing of a proportion of our existing properties Our target is to provide a minimum of 5 apprenticeships under the MHC 15/18 funded programme and existing programmes. | P Y P | 11/15 AHP 100% of the reduced 213 unit programme was completed by 31st March 2015. MHC BTP 93% of this programme is on site and 7% is now complete due to Park View completing ahead of programme in March 15'. This programme has increased since the first allocation; we are now delivering 160 homes compared to the 77 unit allocation we first received. All schemes in this programme are forecast to complete by March 2016. MHC 15/18 6 units are on site 91 units are identified but not yet secured, and are awaiting planning consent. We remain confident we will deliver the programme by March 2018 Our overall Performance across the 3 programmes Expenditure – 105% Starts on site - 100% Completions – 76% 11/15 AHP - We have generated the required pro rata'd conversion income for this programme. MHC BTP - We have generated the required pro rata'd conversion income for this programme. MHC 15/18 - We have so far generated 25% of the required subsidy for this programme. We are ahead of forecast. 11/15 AHP - We have secured 1 apprentice placement across 2 schemes (Davidson and Virgo F) MHC BTP - We have secured 2 apprentice placements (London Rd and King’s Highway). MHC 15/18 – No secured yet due to the lack of secured sites. However, we now have a contractual requirement for all schemes to either deliver a placement directly (if the site is large enough) or via an agency. We expect to exceed our commitment to the GLA of 2 places. |
| i. | To build homes that are environmentally sustainable. | Our target is to build 171 homes to Code for Sustainable Homes (CSH) level 4 and 72 to CSH 3 under the existing programmes | Y | The target is anticipated to be met with the completion of the MHC BTP programme |
|  |  | Our target is to achieve the GLA CO2 reduction target of 40% above 2010 Building Regulations in our MHC 15/18 funded programme. | Y/ongoing | Our project brief identifies that developments should be designed in accordance with the London Plan energy hierarchy which also targets a CO2 reduction of 40% above 2010 Building Regulations |
| j. | To work with our NHS and Local Authority partners re: innovations in the provision of care. | We will review the models of care in our care homes and more widely explore ideas and opportunities for Hexagon to contribute to the NHS and Social Care transformation agenda e.g. personalised services, enabling people to live as independently as possible in their communities. | Y | We are developing a new mental health peer mentor service in Southwark to support sustainability of residents in independent living. We are remodelling our Townley Road care home to a supported living service to support sustainability and independent living. |
| k. | Maintain good working relationships with our Local Authority partners. | Our target is to have representation at relevant HA group meetings and to complete and submit LA performance information forms on time. | Y | We are well represented in the relevant HA group meetings and have had no complaints about late submissions. |
| l. | Provide good quality homes that our residents want to live in. | Our target is to improve resident satisfaction with the defects service by 5% between 2014 and 2017. | P | The baseline measure has now been established via a survey carried out in Jan 2015 to be 80%, but it is too early to report on improvements. However, a new defects system is now in place which will assist in delivering improvements. |

IV.	CROSS CUTTING WORK/ACTIVITIES

|  | Objectives | Targets and Initiatives | Target achieved? (Y for Yes, N for No, or P for partially achieved | Comments |
| --- | --- | --- | --- | --- |
| a. | To implement our Equality and Diversity Policy. | We will implement our Equality and Diversity Action Plan, and develop our Performance Indicators across all diversity strands. Progress will be monitored and driven forward by our Equality and Diversity Working Group, and progress will be reported to the Board annually. | P P | PIs developed and timetable agreed. Work continuing on extending collection of data across all diversity strands, and agreeing targets. DWG monitoring progress. Report to the Board to be prepared for January 16. |
| b. | To maximise Value for Money. | Having implemented the 11-14 Value for Money Strategy, we will develop a further 3 year strategy for 14-17. This strategy will again contain a suite of SMART targets for services where benchmarking indicated that we can do better in terms of cost, quality and return on assets. All targets are to be achieved within the timescales given in the Strategy. | Y | 14-17 VFM strategy was approved by the Board in May 14 |
|  |  | We will report progress on the Value for Money Strategy every year, both to the Board and to our residents. | Y | Progress against the 11/14 strategy was reported to the Board in September 2014. The first progress report on the 14/17 VFM strategy is due in September 2015. |
|  |  | We will undertake and publish an annual self assessment of how Hexagon delivers value of money, in full compliance with the Regulatory Standard. | Y | A self assessment for 13/14 was published on Hexagon’s website in September 14, with a summary in the 13/14 financial statements. As far as we are aware, the assessment meets the Regulatory Standard. |
| c. | To pursue joint procurement activities wherever possible with other Housing Associations where this assists with economies of scale and savings. | To work closely with our peer groups on opportunities to save VAT, increase purchasing power, framework procurement exercises and e auctions where appropriate. | Y | Cyclical painting programme; asbestos surveys and internal works have been procured via the SEC framework. All procurement assesses SEC and PfH frameworks before tendering for the larger contracts. Continued full involvement in the framework procurement carried out by SEC |
| d. | To minimise the harm that our business does to the environment. | We will maintain a sustainability strategy that is designed to minimise our impact on the environment, meeting annual targets and objectives approved by the board. | Y | The targets in the strategy have been met to date. Sustainable Homes benchmark over 2m properties and the cross references and support within the Sustainability and Greening the Stock strategies added weight to our Shift Gold award in 2014 |
| e. | To ensure that the Housing Regulator maintains a high level of confidence in Hexagon. | Our target is to continue to achieve the highest HCA ratings possible in relation to governance and financial viability. | Y | The HCA viability review issued in March 2015 confirmed that we have retained our V1 rating and our Governance rating has remained at G1 (both highest possible grades) |
| f. | To ensure we communicate clearly and effectively with the wide range of stakeholders that have an interest in Hexagon’s business, our performance, and our achievements. | We will implement an annual action plan arising from our Communications Strategy via our in-house Communications Working Group. | Y | The Communications Working Group meets regularly to ensure the Communications Strategy is implemented as planned and we have delivered the entire plan, including for example, the launch of the new website. |